## Test Cases
TC ID | Bug ID | Module | Test Case Title | Test Steps | Expected Result | Priority | Status | Actual Result | Remarks
TC-001 | BUG-001 | Frontend | Verify spacing above the Dosage Guide cards is correct | 1. Navigate to the screen containing the Dosage Guide cards. 2. Check the spacing above the cards. | Spacing above the Dosage Guide cards is correct and not excessive, matching the design specification. | Low | Failed | Excessive spacing still appears above the Dosage Guide cards. | Bug still marked "Open" in bug report — retest once fix is deployed.
TC-002 | BUG-002 | Frontend | Verify columns in the Discover More section are properly sized | 1. Navigate to the Discover More section. 2. Check the sizing/alignment of the columns. | Columns in the Discover More section are properly and consistently sized as per design. | Low | Failed | Columns in the Discover More section are still not properly sized. | Bug still marked "Open" in bug report — retest once fix is deployed.
TC-003 | BUG-003 | Frontend | Verify spacing is present before the Full Name field on the Sign Up screen | 1. Navigate to the Sign Up screen. 2. Check the spacing above/before the Full Name field. | Correct spacing is present before the Full Name field, matching the design. | Low | Failed | Spacing is still missing before the Full Name field on the Sign Up screen. | Bug still marked "Open" in bug report — retest once fix is deployed.
TC-004 | BUG-004 | Frontend | Verify only the back arrow is clickable in the back navigation row on Sign Up | 1. Navigate to the Sign Up screen. 2. Click on the back arrow row but away from the arrow icon itself. 3. Click directly on the back arrow icon. | Clicking elsewhere on the row does not trigger back navigation; only clicking the back arrow icon triggers it. | Medium | Failed | Clicking anywhere on the back arrow row still triggers back navigation, not just the arrow itself. | Bug still marked "Open" in bug report — retest once fix is deployed.
TC-005 | BUG-005 | Frontend | Verify Terms & Conditions link is present on the Sign Up screen | 1. Navigate to the Sign Up screen. 2. Check for the Terms & Conditions link. 3. Click the link. | Terms & Conditions link is present and correctly navigates to the Terms & Conditions content. | Medium | Failed | Terms & Conditions link is still missing on the Sign Up screen. | Bug still marked "Open" in bug report — retest once fix is deployed.
TC-006 | BUG-006 | Frontend | Verify Privacy Policy link is present on the Sign Up screen | 1. Navigate to the Sign Up screen. 2. Check for the Privacy Policy link. 3. Click the link. | Privacy Policy link is present and correctly navigates to the Privacy Policy content. | Medium | Failed | Privacy Policy link is still missing on the Sign Up screen. | Bug still marked "Open" in bug report — retest once fix is deployed.
TC-007 | BUG-007 | Backend | Verify purchased plan name is displayed on the Profile screen | 1. Log in as a user who has purchased a plan. 2. Navigate to the Profile screen. 3. Check for the purchased plan name. | Purchased plan name is correctly displayed on the Profile screen. | High | Failed | Purchased plan name is still not displayed on the Profile screen. | Bug still marked "Open" in bug report — retest once fix is deployed.
TC-008 | BUG-008 | Frontend | Verify "Archived" text is replaced with "Saved" | 1. Navigate to the screen previously showing "Archived". 2. Check the displayed label text. | Label correctly reads "Saved" instead of "Archived". | Low | Failed | Text still shows "Archived" instead of "Saved". | Bug still marked "Open" in bug report — retest once fix is deployed.
TC-009 | BUG-009 | Frontend | Verify the required screen is present and accessible | 1. Navigate through the app flow to reach the point where the screen should appear. 2. Check whether the screen is present. | Required screen is present and accessible at the correct point in the flow. | High | Failed | Required screen is still missing from the flow. | Bug still marked "Open" in bug report — retest once fix is deployed.
TC-010 | BUG-010 | Frontend | Verify the "You" label is not displayed in the AI Chat | 1. Navigate to the AI Chat screen. 2. Send a message as the user. 3. Check for a "You" label next to the message. | "You" label is not displayed in the AI Chat for user messages. | Low | Failed | "You" label is still displayed in the AI Chat. | Bug still marked "Open" in bug report — retest once fix is deployed.
TC-011 | BUG-011 | Frontend | Verify AI Chat has a Scroll to Bottom button | 1. Navigate to the AI Chat screen. 2. Scroll up through the chat history. 3. Check for a Scroll to Bottom button/option. | Scroll to Bottom button is present and correctly scrolls the chat to the latest message when tapped. | Medium | Failed | AI Chat is still missing a Scroll to Bottom button. | Bug still marked "Open" in bug report — retest once fix is deployed.
TC-012 | BUG-012 | Frontend | Verify clicking Explore More Peptides does not show Page Not Found | 1. Navigate to the relevant screen. 2. Click "Explore More Peptides". | App navigates to the correct Explore More Peptides page without showing a Page Not Found error. | High | Failed | Clicking Explore More Peptides still displays a Page Not Found error. | Bug still marked "Open" in bug report — retest once fix is deployed.

## Summary
Peptide - Test Case Summary
Total Bugs Covered | 12
Total Test Cases | 12
Frontend Module Bugs | 11
Backend Module Bugs | 1
High Priority | 3
Medium Priority | 4
Low Priority | 5
Passed | 0
Failed | 12